## Instructions (hidden)
Instructions
1 | Orint out field sheets from the "print copy" tab
2 | Select OC to commence data collection from
3 | Using the Control Room Contractor sign on board as a start, establish the starting point for the days event
4 | Starting from the control room, move out into the OC and make contact with every Contractor Work Group that you come across
5 | For every contact, record the below information as a separate observation on the "Data_Log" tab
| Date | Observation Time | Purchase Order Number | RCS Number | Work Order Number | Job Start Time | Job Finish Time | Work group | OC | Authority To Proceed Description | Alcoa Responsible Person | Contractor Responsible Person | Does ARP walk the job. In the alloted time frames | Field Verifications Completed (ARP) | Field Verifications Completed (CRP) | Supervision Present | Name Of Supervisor | Names Of People On Job 1 | Names Of People On Job 2 | Names Of People On Job 3 | Names Of People On Job 4 | Names Of People On Job 5 | Names Of People On Job 6 | Names Of People On Job 7 | Names Of People On Job 8 | Names Of People On Job 9 | Names Of People On Job 10 | Equipment On Job 1 | Equipment On Job 2 | Equipment On Job 3 | Equipment On Job 4 | Equipment On Job 5 | Equipment On Job 6 | Equipment On Job 7 | Equipment On Job 8 | Equipment On Job 9 | Equipment On Job 10
Note | Do not append each job observation to the one entry. If an observation is made on the same job four times, then there shall be 4 separate observations captured
6 | Capture general observations observed throughout each day on the "Observations made" tab
Note on B7: Cullen, Joshua: Date Format Short DD/MM
Note on C7: Cullen, Joshua: 24hr (HH:MM)
Note on F7: Cullen, Joshua: Work Orders can be: (a) 1234567 or (b) WO1234567 or a Project Number (c) PIN0001234567
Note on G7: Cullen, Joshua: 24hr (HH:MM)
Note on H7: Cullen, Joshua: 24hr (HH:MM)
Note on O7: Cullen, Joshua: Yes or No
Note on P7: Cullen, Joshua: Yes or No
Note on Q7: Cullen, Joshua: Yes or No
Note on AC7: Cullen, Joshua: Restrict Equipment to Vehicles (ute, truck, HPW unit & size, VAC truck and anything else worth noting)

## Data_Log
Date | Observation Time | Purchase Order Number | RCS Number | Work Order Number | Job Start Time | Job Finish Time | Work group | Risk | OC | Authority To Proceed Description | Does ARP walk the job. In the alloted time frames | Field Verifications Completed (ARP) | Field Verifications Completed (CRP) | Supervision Present | # of People on Job
2021-07-05 | 10:45 | 7175923 |  | 2285000 | 10:00 |  | Kaefer | Low | 1 | Set up welder and spools for capital projects | No | Yes | Yes | No | 3
2021-07-05 | 11:49 | 7180602 |  |  | 11:00 | 12:00 | Cleanaway | Medium | 1 | 108w drain. vacuum out pit. N/E. of car park | No | Yes | Yes | No | 2
2021-07-05 | 13:00 | 7180602 |  |  | 13:00 | 14:00 | Cleanaway | Medium | 1 | 108w drain. vacuum out pit. N/W. of car park | No | Yes | Yes | No | 4
2021-07-05 | 8:50 | 7181286 | 90145 |  | 8:00 |  | Cleanaway | High | 1 | HPW clean vent lines | No | Yes | Yes | No | 2
2021-07-05 | 8:40 | 7181625 | 87318 |  | 8:45 |  | UGL Scaff | High | 1 | Erect scaffold #51 Blow off tank | No | Yes | Yes | No | 2
2021-07-05 | 9:00 | 7190455 | J002450 |  | 8:20 |  | Impact Engineering | Medium | 1 | 30E Heater repairs | No | Yes | Yes | Yes | 3
2021-07-05 | 8:45 | 7190673 |  |  | 8:00 |  | Cleanaway | Medium | 1 | Bog out lake duck | No | Yes | Yes | No | 2
2021-07-05 | 8:30 | 47119140 | 90477 |  | 8:00 |  | UGL Elec | Low | 1 | Connect fume extractors mills workshop | No | Yes | Yes | No | 2
2021-07-05 | 8:35 | 7154232cs | 85039 |  | 8:30 |  | Altrad | Medium | 1 | Repair insulation PFT #31 | No | Yes | Yes | No | 2
2021-07-05 | 8:55 | 7190400cs | 92237 |  | 8:00 |  | Enermech | High | 1 | Install hot tap HPW blast valve | No | Yes | Yes | Yes | 6
2021-07-06 | 13:30 | 7159052 | 85909 |  | 8:30 | 14:29 | Thor | Medium | 1 | Remove concrete from 51 MPP base | Yes | Yes | Yes | No | 1
2021-07-06 | 11:50 | 7188654 |  |  | 8:00 |  | ALS | Low | 1 | Sub station thermal checks on cabinets | Yes | Yes | Yes | No | 2
2021-07-06 | 9:55 | 7185097 |  |  | 9:30 |  | Cleanaway | Medium | 1 | Vacuum #56 sump pit | Yes | Yes | Yes | No | 2
2021-07-06 | 7:45 | 7190400 | 92237 |  | 7:30 |  | Enermech | High | 1 | HPW clean Steam valve 30 unit #4 | No | Yes | Yes | Yes | 3
2021-07-06 | 8:10 | 7190455 | J002450 |  | 7:30 | 14:45 | Impact Engineering | Medium | 1 | Repair heater 30E | No | Yes | Yes | Yes | 4
2021-07-06 | 8:03 | 7175923 |  | 2285000 | 8:00 |  | Kaefer | High | 1 | Insert Tee piece in slurry line 30 unit 4 | Yes | Yes | Yes | No | 2
2021-07-06 | 7:35 | 4144977710 | 92313 |  | 7:30 |  | UGL Rope | High | 1 | #51 B.O.T. Descale | Yes | Yes | Yes | No | 4
2021-07-06 | 7:30 | 718397 | 90142 |  | 7:30 |  | UGL Scaff | High | 1 | 34 digester bank service | Yes | Yes | Yes | No | 2
2021-07-06 | 10:30 |  | 92319 |  | 10:00 | 14:00 | UGL Scaff | Medium | 1 | Erect scaffold #42 MPP disch. valve | Yes | Yes | Yes | No | 2
2021-07-06 | 10:08 | 7188653 |  |  | 10:20 | 13:00 | Veolia | Medium | 1 | Repair leak in pipe 25c | Yes | Yes | Yes | No | 2
2021-07-06 | 11:40 |  | 92345 |  | 10:30 | 11:44 | Veolia | Medium | 1 | Repair piping 25A2 | Yes | Yes | Yes | No | 2
2021-07-07 | 8:15 | 7154232 | 85039 |  | 7:45 |  | Altrad | High | 1 | Install Cladding #31 PFT | Yes | Yes | Yes | No | 3
2021-07-07 | 10:20 | 7154232 | 85039 |  | 7:45 |  | Altrad | High | 1 | Install Cladding #31 PFT | Yes | Yes | Yes | No | 3
2021-07-07 | 13:15 | 7154232 | 85039 |  | 7:45 |  | Altrad | High | 1 | Install Cladding #31 PFT | Yes | Yes | Yes | No | 1
2021-07-07 | 11:00 | 7185097 |  |  | 10:30 |  | Cleanaway | Medium | 1 | Clear scale around #56 sump pit | No | Yes | Yes | No | 2
2021-07-07 | 13:05 | 7185097 |  |  | 10:30 |  | Cleanaway | Medium | 1 | Clear scale around #56 sump pit | No | Yes | Yes | No | 2
2021-07-07 | 14:10 | 7185097 |  |  | 10:30 |  | Cleanaway | Medium | 1 | Clear scale around #56 sump pit | No | Yes | Yes | No | 2
2021-07-07 | 8:20 | 7191412 |  |  | 7:45 | 9:30 | Impact Engineering | Medium | 1 | #22 heater repair. Bld 30 | No | Yes | Yes | No | 4
2021-07-07 | 12:10 | 7191412 |  |  | 12:00 |  | Impact Engineering | Medium | 1 | Repair #26 Heater | No | Yes | Yes | No | 4
2021-07-07 | 8:07 | 7175923 |  |  | 7:30 |  | Kaefer | High | 1 | Insert Tee piece in slurry line 30 unit 4 | Yes | Yes | Yes | No | 3
2021-07-07 | 10:00 | 7175923 |  |  | 7:30 |  | Kaefer | High | 1 | Insert Tee piece in slurry line 30 unit 4 | Yes | Yes | Yes | No | 3
2021-07-07 | 13:45 | 7175923 |  |  | 7:30 |  | Kaefer | High | 1 | Insert Tee piece in slurry line 30 unit 4 | Yes | Yes | Yes | No | 3
2021-07-07 | 10:25 | 7183573 |  |  | 7:00 |  | UGL Mech | High | 1 | Install tapping points #56 contact heater | Yes | Yes | Yes | No | 2
2021-07-07 | 12:10 | 7183573 |  |  | 7:00 |  | UGL Mech | High | 1 | Install tapping points #56 contact heater | Yes | Yes | Yes | No | 2
2021-07-07 | 13:40 | 7183573 |  |  | 7:00 |  | UGL Mech | High | 1 | Install tapping points #56 contact heater | Yes | Yes | Yes | No | 2
2021-07-07 | 7:51 |  | 92313 | 4144977-10 | 7:30 | 11:30 | UGL Rope | High | 1 | Descale #51 BOT Relief line | Yes | Yes | Yes | No | 5
2021-07-07 | 9:00 |  | 92313 | 4144977-10 | 7:30 | 11:30 | UGL Rope | High | 1 | Descale #51 BOT Relief line | Yes | Yes | Yes | No | 5
2021-07-07 | 10:00 | 230399 | 91720 |  | 10:00 |  | UGL Scaff | High | 1 | Build scaffold 42 unit #1 | Yes | Yes | Yes | No | 2
2021-07-07 | 13:20 | 7181625 | 87318 |  | 11:00 |  | UGL Scaff | High | 1 | Install internal scaff. internal #51 flash tank | No | Yes | Yes | No | 4
2021-07-07 | 7:52 | 7181625 | 87318 |  | 7:30 |  | UGL Scaff | Medium | 1 | Erect external scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-07 | 9:10 | 7181625 | 87318 |  | 7:30 |  | UGL Scaff | Medium | 1 | Erect external scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-07 | 13:38 | 7181625 | 87318 |  | 7:30 |  | UGL Scaff | Medium | 1 | Erect external scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-07 | 11:15 | 7181625 | 87318 |  | 11:00 |  | UGL Scaff | High | 1 | Install internal scaff. internal #51 flash tank | No | Yes | Yes | No | 4
2021-07-07 | 12:00 | 7181625 | 87318 |  | 11:00 |  | UGL Scaff | High | 1 | Install internal scaff. internal #51 flash tank | No | Yes | Yes | No | 4
2021-07-07 | 8:00 | 7183397 | 90142 |  | 7:30 | 9:16 | UGL Scaff | Medium | 1 | Build scaffolds to cones of #34 digester bank | No | Yes | Yes | No | 4
2021-07-07 | 9:00 | 7183397 | 90142 |  | 7:03 | 9:16 | UGL Scaff | Medium | 1 | Build scaffolds to cones of #34 digester bank | No | Yes | Yes | No | 4
2021-07-07 | 12:00 | 7190324 | 84802 |  | 7:00 |  | UGL Scaff | High | 1 | Erect scaffold to alarm spool 30 unit #1 | No | Yes | Yes | No | 2
2021-07-07 | 10:00 | 7190325 | 84802 |  | 7:00 |  | UGL Scaff | High | 1 | Erect scaffold to alarm spool 30 unit #1 | No | Yes | Yes | No | 2
2021-07-07 | 8:00 | 7190325 | 84802 |  | 7:00 |  | UGL Scaff | High | 1 | Erect scaffold to alarm spool 30 unit #1 | Yes | Yes | Yes | No | 2
2021-07-07 | 12:15 | 7191276 |  |  | 11:00 |  | UGL Scaff | High | 1 | Erect scaffold #16 heater | Yes | Yes | Yes | No | 2
2021-07-07 | 14:07 | 7191276 |  |  | 11:00 |  | UGL Scaff | High | 1 | Erect scaffold #16 heater | Yes | yes | Yes | No | 2
2021-07-08 | 8:00 |  | 82775 | 4302013 | 8:00 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 2
2021-07-08 | 11:50 |  | 82775 | 4302013 | 8:00 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 2
2021-07-08 | 13:05 |  | 82775 | 4302013 | 8:00 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 2
2021-07-08 | 9:22 | 7178513 |  |  | 7:30 |  | Cleanaway | High | 1 | Descale #34 Sand trap | Yes | No | Yes | No | 4
2021-07-08 | 13:35 | 7191815 |  |  | 11:30 |  | Cleanaway | High | 1 | Vacuum & jet wash 25 feed conveyors silt pit | No | Yes | Yes | No | 2
2021-07-08 | 14:15 | 7191815 |  |  | 11:30 |  | Cleanaway | High | 1 | Vacuum & jet wash 25 feed conveyors silt pit | No | Yes | Yes | No | 2
2021-07-08 | 9:15 | 7191412 |  |  | 8:00 |  | Impact Engineering | Medium | 1 | #22 heater repairs | No | No | Yes | Yes | 3
2021-07-08 | 7:45 | 7173834 |  |  | 7:30 |  | Kaefer | Low | 1 | Measure diameter of #5 containment tank | Yes | Yes | Yes | No | 2
2021-07-08 | 9:15 | 7173834 |  |  | 7:30 | 10:00 | Kaefer | Low | 1 | Measure diameter of #5 containment tank | Yes | Yes | Yes | No | 4
2021-07-08 | 13:20 | 7175923 |  |  | 13:00 |  | Kaefer | High | 1 | Install bypass Bld. 30 | No | No | No | No | 1
2021-07-08 | 7:30 | 7175923 |  |  | 7:00 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 4
2021-07-08 | 9:00 | 7175923 |  |  | 9:00 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | Yes | 4
2021-07-08 | 7:35 | 7183573 | SOW |  | 7:00 |  | UGL Mech | High | 1 | Install hot taps #56 contact heater | Yes | Yes | Yes | No | 3
2021-07-08 | 9:15 | 7183573 | SOW |  | 7:00 |  | UGL Mech | High | 1 | Install hot taps #56 contact heater | Yes | Yes | Yes | No | 3
2021-07-08 | 11:15 | 7183573 | SOW |  | 7:00 |  | UGL Mech | High | 1 | Install hot taps #56 contact heater | Yes | Yes | Yes | No | 3
2021-07-08 | 8:30 | 7189318 | 90578 |  | 7:10 |  | UGL Rope | High | 1 | C/out popper on steam line 25a STL #7 | No | Yes | Yes | No | 2
2021-07-08 | 9:45 | 7181625 | 87318 |  | 9:45 |  | UGL Scaff | High | 1 | Internal scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-08 | 13:56:00 PM | 7181625 | 87318 |  | 13:15 |  | UGL Scaff | High | 1 | Internal scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-08 | 11:00 | 7181625 | 87318 |  | 11:06 |  | UGL Scaff | High | 1 | Internal scaffold #51 B.O.T. | No | Yes | Yes | No | 3
2021-07-09 | 10:30 | 7175923 |  |  | 7:00 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 6
2021-07-09 | 12:10 | 7178513 |  |  | 8:00 |  | Cleanaway | High | 1 | Descale #34 Sand trap | No | No | No | No | 3
2021-07-09 | 13:00 | 7178513 |  |  | 8:00 |  | Cleanaway | High | 1 | Descale #34 Sandtrap | No | No | No | No | 2
2021-07-09 | 14:00 | 7178513 |  |  | 8:00 |  | Cleanaway | High | 1 | Descale #34 Sandtrap | No | No | No | No | 2
2021-07-09 | 10:30 | 7178513 |  |  | 8:00 |  | Cleanaway | High | 1 | Descale #34 Sand trap | No | Yes | Yes | No | 1
2021-07-09 | 8:02 | 7178513 |  |  | 8:00 |  | Cleanaway | High | 1 | Descale #34 Sand trap | No | Yes | Yes | No | 3
2021-07-09 | 10:05 | 7191412 |  |  | 8:20 |  | Impact Engineering | High | 1 | #22 heater repairs | Yes | Yes | Yes | Yes | 3
2021-07-09 | 12:13 | 7191412 |  |  | 8:20 |  | Impact Engineering | High | 1 | #22 heater repairs | Yes | Yes | Yes | Yes | 3
2021-07-09 | 14:00 | 7191412 |  |  | 8:20 |  | Impact Engineering | High | 1 | #22 heater repairs | Yes | Yes | Yes | Yes | 3
2021-07-09 | 7:44 |  | 82775 | 4302013 | 7:45 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 3
2021-07-09 | 10:35 |  | 82775 | 4302013 | 7:45 |  | ALS | medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 3
2021-07-09 | 8:17 | 7191412 |  |  | 8:20 |  | Impact Engineering | Medium | 1 | #22 heater repairs | Yes | Yes | Yes | Yes | 3
2021-07-09 | 8:40 | 7175923 |  |  | 8:40 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 6
2021-07-09 | 10:45 | 7175923 |  |  | 8:40 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 6
2021-07-09 | 11:59 | 7171054 | 83341 |  | 11:20 | 13:00 | UGL Scaff | High | 1 | #11 digester bank service | No | Yes | Yes | No | 2
2021-07-09 | 8:30 | 7183397 | 90112 |  | 7:30 |  | UGL Scaff | High | 1 | #34 digester bank service | No | Yes | Yes | No | 2
2021-07-12 | 8:00 | 7175923 |  |  | 7:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 3
2021-07-12 | 14:30 | 7175923 |  |  | 14:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 2
2021-07-12 | 13:50 | 7181625 | 87318 |  | 11:00 | 14:00 | UGL Scaff | High | 1 | Modify scaffold #51 B.O.T. | Yes | Yes | Yes | No | 1
2021-07-12 | 7:00 | 7183573 |  |  | 7:00 | 10:00 | UGL Mech | High | 1 | Install ball valves #56 contact heater | Yes | Yes | Yes | No | 2
2021-07-12 | 13:35 | 7188448 | 91701 |  | 10:30 |  | Veolia | High | 1 | Drill holes #34 S/Trap tank stiffener | Yes | Yes | Yes | No | 3
2021-07-12 | 14:35 | 7188448 | 91071 |  | 10:30 | ? | Veolia | High | 1 | Drill holes #34 S/Trap tank stiffener | Yes | Yes | Yes | No | 3
2021-07-12 | 13:40 | 7188546 |  |  | 9:30 |  | ALS Ropes | High | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | Yes | 2
2021-07-12 | 8:18 | 7191209 | 92346 |  | 8:00 |  | Konecranes | High | 1 | Replace pendant 108W pedestal crane | Yes | Yes | Yes | No | 1
2021-07-12 | 11:06 | 7191209 | 92346 |  | 8:00 | 12:00 | Konecranes | High | 1 | Replace pendant 108W pedestal crane | Yes | Yes | Yes | No | 1
2021-07-12 | 8:45 | 7192350 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners 11a digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 11:25 | 7192350 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners 11a digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 13:30 | 7192350 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners 11A Digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 8:44 | 7192351 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 11:25 | 7192351 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 13:30 | 7192351 |  |  | 6:30 |  | UGL Mech | High | 1 | Install liners in 11B Digester vessel | Yes | Yes | Yes | No | 3
2021-07-12 | 11:45 | 7188546CS |  |  | 9:30 |  | ALS Ropes | High | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | Yes | 2
2021-07-12 | 9:48 | 7162002 |  |  |  |  | UGL Elec | Medium | 1 | Rewire S.A.S in Sub station #14 | No | No | Yes | No | 2
2021-07-12 | 13:25:00 PM | 7162002 |  |  | 6:30 | 13:30 | UGL Elec | Medium | 1 | Rewire S.A.S in Sub station #14 | No | No | Yes | No | 1
2021-07-12 | 13:30 | 7182641 | 82775 |  | 8:00 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 1
2021-07-12 | 7:30 | 7185365 |  |  | 8:00 |  | ALS | Medium | 1 | Test cone #31 sand trap | No | Yes | Yes | No | 2
2021-07-12 | 10:00 | 7185365 |  |  | 8:00 | 11:15 | ALS | Medium | 1 | Test cone #31 sand trap | No | Yes | Yes | No | 2
2021-07-12 | 9:15 | 7189798 |  |  | 9:20 |  | Impact Engineering | Medium | 1 | Repair #55 Heater | Yes | Yes | Yes | Yes | 3
2021-07-12 | 11:30 | 7189798 |  |  | 9:20 |  | Impact Engineering | Medium | 1 | Repair #55 Heater | Yes | Yes | Yes | Yes | 3
2021-07-12 | 14:00 | 7189798 |  |  | 9:00 |  | Impact Engineering | Medium | 1 | Repair #55 Heater | Yes | Yes | Yes | Yes | 3
2021-07-12 | 7:50 | 715693805 | 84670 |  | 8:00 |  | ALS | Medium | 1 | Inspect cone liners #21 GCH 25C | Yes | Yes | Yes | No | 2
2021-07-13 | 14:50 | 71759 |  |  | 8:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 2
2021-07-13 | 8:43 | 7170506 |  |  | 8:00 |  | Cleanaway | High | 1 | HPW clean #51B.O.T. vapour line | Yes | Yes | Yes | No | 3
2021-07-13 | 11:05 | 7170506 |  |  | 8:00 |  | Cleanaway | High | 1 | HPW clean #51B.O.T. vapour line | Yes | Yes | Yes | No | 0
2021-07-13 | 11:59 | 7170506 |  |  | 8:00 |  | Cleanaway | High | 1 | HPW clean #51B.O.T. vapour line | Yes | Yes | Yes | No | 3
2021-07-13 | 13:55 | 7170506 |  |  | 8:00 | 14:00 | Cleanaway | High | 1 | HPW clean #51B.O.T. vapour line | Yes | Yes | Yes | No | 3
2021-07-13 | 8:50 | 7175923 |  |  | 8:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 2
2021-07-13 | 11:05 | 7175923 |  |  | 8:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 2
2021-07-13 | 14:17 | 7175923 |  |  | 8:30 |  | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 0
2021-07-13 | 11:48 | 7180427 |  |  | 7:30 |  | UGL Rope | High | 1 | Patch #6 mill feed bin wall | Yes | Yes | Yes | No | 3
2021-07-13 | 13:15:00 PM | 7180427 |  |  | 7:30 |  | UGL Rope | High | 1 | Patch #6 mill feed bin wall | Yes | Yes | Yes | No | 3
2021-07-13 | 12:14 | 7185111 |  |  | 12:15 | 12:30 | S.R.E. | High | 1 | Check cable tray lanyards | Yes | Yes | Yes | Yes | 2
2021-07-13 | 7:45 | 7192350 |  |  | 8:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-13 | 11:00 | 7192350 |  |  | 8:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-13 | 14:10 | 7192350 |  |  | 8:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-13 | 8:20 | 7192351 |  |  | 8:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | No | 5
2021-07-13 | 11:00 | 7192351 |  |  | 8:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | yes | Yes | Yes | 5
2021-07-13 | 14:10 | 7192351 |  |  | 8:00 |  | UGL Mech | High | 1 | 1nstall liners 11B digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-13 | 8:15 | 713559 |  |  | 8:20 |  | ALS | Medium | 1 | Routine Vibration testing 25A/25C | No | Yes | Yes | No | 1
2021-07-13 | 10:30 | 713559 |  |  | 8:20 |  | ALS | Medium | 1 | Routine vibration monitoring | No | Yes | Yes | No | 1
2021-07-13 | 14:12 | 713559 |  |  | 8:20 |  | ALS | Medium | 1 | Routine vibration monitoring | No | Yes | Yes | No | 1
2021-07-13 | 11:41 | 7174271 | 88130 |  | 8:55 |  | Impact Engineering | Medium | 1 | #6 mill girth gear inspection | No | Yes | Yes | Yes | 2
2021-07-13 | 13:20 | 7174271 | 88130 |  | 8:55 |  | Impact Engineering | Medium | 1 | #6 mill girth gear inspection | No | Yes | Yes | Yes | 2
2021-07-13 | 9:18 | 7174721 | 88130 |  | 8:55 |  | Impact Engineering | Medium | 1 | #6 mill girth gear inspection | No | Yes | Yes | Yes | 2
2021-07-13 | 10:05 | 7189798 |  |  | 8:00 |  | Impact Engineering | Medium | 1 | #55 heater repairs | No | Yes | Yes | No | 2
2021-07-13 | 8:07 | 7189798 |  |  | 8:00 |  | Impact Engineering | Medium | 1 | #55 heater repairs | No | Yes | Yes | Yes | 3
2021-07-13 | 10:56 | 7189798 |  |  | 8:00 |  | Impact Engineering | Medium | 1 | #55 heater repairs | No | Yes | Yes | Yes | 4
2021-07-13 | 10:00 | 7191412 |  |  | 10:00 |  | Impact Engineering | Medium | 1 | #22 heater repairs | Yes | Yes | Yes | Yes | 2
2021-07-13 | 14:00 | 7193332 |  |  | 14:15 |  | Impact Engineering | Medium | 1 | 11/1 Bld. 42 heater repairs | No | Yes | Yes | Yes | 4
2021-07-13 | 8:29 |  | 82775 | 4302013 | 8:30 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 1
2021-07-13 | 10:45 |  | 82775 |  | 8:29 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | Yes | Yes | No | 1
2021-07-13 | 14:15 |  | 82775 | 4302013 | 8:30 |  | ALS | Medium | 1 | Routine thickness testing Bld 30 | No | yes | Yes | No | 1
2021-07-14 | 14:30 | 7183397 | 90142 |  | 7:00 | 15:00 | Altrad | High | 1 | Remove asbestos gaskets if required | Yes | Yes | Yes | No | 1
2021-07-14 | 7:43 | 7175923 |  |  | 7:30 | 8:30 | Kaefer | High | 1 | Install bypass Bld. 30 | Yes | Yes | Yes | No | 3
2021-07-14 | 7:00 | 7177384 |  |  | 6:30 |  | UGL Scaff | High | 1 | Dismantle scaffolds #34 Digester bank | No | Yes | Yes | Yes | 3
2021-07-14 | 11:00 | 7183397 |  |  | 10:30 |  | UGL Mech | High | 1 | #34 digester bank service | No | Yes | Yes | No | 3
2021-07-14 | 8:00 | 7186385 | 90684 |  | 7:35 |  | UGL Rope | High | 1 | C/out elbow 30 unit #3 | Yes | Yes | Yes | No | 3
2021-07-14 | 14:00 | 7186385 | 90684 |  | 7:35 | 15:00 | UGL Rope | High | 1 | C/ out elbow 30 unit #3 | Yes | Yes | Yes | No | 3
2021-07-14 | 12:05 | 7186385 | 90684 |  | 7:30 |  | UGL Rope | High | 1 | C/out elbow 30 unit #3 | No | Yes | Yes | No | 3
2021-07-14 | 14:15 | 7186959 |  |  | 7:30 |  | Westerfeld | High | 1 | D1/D2 tripper floor repairs | No | No | Yes | Yes | 4
2021-07-14 | 10:08 | 7186959 |  |  | 7:30 |  | Westerfeld | High | 1 | D1/D2 tripper floor repairs | Yes | Yes | Yes | Yes | 4
2021-07-14 | 7:59 | 7192350 |  |  | 7:30 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-14 | 13:42 | 7192350 |  |  | 7:30 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-14 | 8:02 | 7192351 |  |  | 7:30 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-14 | 13:42 | 7192351 |  |  | 7:30 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-14 | 11:25 | 7192851 | 92386 |  | 6:30 |  | UGL Scaff | High | 1 | Erect scaffold #5 mill | No | Yes | Yes | No | 3
2021-07-14 | 13:18 | 7192851 | 92386 |  | 6:30 | 13:18 | UGL Scaff | High | 1 | Erect scaff #5 mill | No | Yes | Yes | No | 3
2021-07-14 | 6:46 |  |  |  | 6:30 |  | UGL Scaff | High | 1 | Erect scaffold #5 mill | No | Yes | Yes | No | 3
2021-07-14 | 13:25 | 7007080 |  |  | 10:00 |  | Delron | Medium | 1 | 108W office cleaning | Yes | Yes | Yes | No | 1
2021-07-14 | 6:34 | 7174721 |  |  | 18:0013/7 | 7:37 | Impact Engineering | Medium | 1 | #6 mill girth gear inspection | Yes | Yes | Yes | Yes | 3
2021-07-14 | 10:00 | 7177384 |  |  | 7:00 |  | UGL Scaff | Medium | 1 | Strip scaffolds #34 Digester bank | No | Yes | Yes | Yes | 3
2021-07-14 | 14:10 | 7193332 |  |  | 7:30 |  | Impact Engineering | Medium | 1 | Repair BLD. 42 11/1 heater | No | Yes | Yes | No | 4
2021-07-14 | 9:20 | 7193332 |  |  | 7:30 |  | Impact Engineering | Medium | 1 | Repair Bld. 42 11/1 heater | No | Yes | Yes | Yes | 3
2021-07-14 | 8:00 | 7193332 |  |  | 7:30 |  | Impact Engineering | Medium | 1 | Repair Bld. 42 11/1 heater | No | Yes | Yes | Yes | 3
2021-07-14 | 7:19 |  | 82775 | 430213 | 7:30 |  | ALS | Medium | 1 | Routine NDT Bld. 30 | No | Yes | Yes | No | 2
2021-07-14 | 9:15 |  | 82775 | 430213 | 7:30 |  | ALS | Medium | 1 | Routine NDT Bld. 30 | No | Yes | Yes | No | 2
2021-07-14 | 10:17 |  |  |  | 10:00 | 10:30 | Robowash | Medium | 1 | Remove waste liquid Mills lube shed | No | Yes | Yes | No | 1
2021-07-15 | 10:37 | 7171533 |  |  | 7:30 |  | UGL Mech | High | 1 | Drill holes for valve safety pins | Yes | Yes | Yes | No | 2
2021-07-15 | 6:58 | 7192350 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-15 | 10:40 | 7192350 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11A digster vessel | Yes | Yes | Yes | Yes | 4
2021-07-15 | 14:20 | 7192350 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 4
2021-07-15 | 6:58 | 7192351 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 2
2021-07-15 | 10:40 | 7192351 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 2
2021-07-15 | 14:20 | 7192351 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 2
2021-07-15 | 8:25 | 7171053 | 85959 | 10:00 | 8:00 |  | ALS | Medium | 1 | Check cone repairs #11 digester bank. NDT | Yes | Yes | Yes | No | 1
2021-07-15 | 10:35 | 7183396 | 90135 |  | 10:30 |  | ALS | Medium | 1 | NDT on #34 Digester bank cones | Yes | Yes | Yes | No | 1
2021-07-15 | 12:34 | 7189811 | 82356-7 |  | 12:30 | 13:50 | ECM | Medium | 1 | Airconditioner Maintenance | Yes | Yes | Yes | Yes | 1
2021-07-15 | 12:34 | 7189819 | 82408-7 |  | 12:30 | 13:50 | ECM | Medium | 1 | Airconditioner Breakdowns | Yes | Yes | Yes | Yes | 1
2021-07-15 | 10:30 | 7191421 | 91925 |  | 7:20 |  | Thor | Medium | 1 | Paint walls 30X | Yes | Yes | Yes | No | 2
2021-07-15 | 13:40 | 7191421 | 91925 |  | 7:20 |  | Thor | Medium | 1 | Paint walls 30X | Yes | Yes | Yes | No | 2
2021-07-15 | 7:36 | 7192452 | 82775 |  | 7:30 |  | ALS | Medium | 1 | NDT on live steam heater heads Bld. 30 | No | Yes | Yes | No | 1
2021-07-15 | 10:35 | 7192452 | 82775 |  | 7:36 |  | ALS | Medium | 1 | NDT on live steam heater heads Bld. 30 | No | Yes | Yes | No | 1
2021-07-15 | 13:50 | 7192452 | 82775 |  | 7:36 |  | ALS | Medium | 1 | NDT on live steam heater heads Bld. 30 | No | Yes | Yes | No | 1
2021-07-15 | 8:50 | 7193332 |  |  | 8:50 |  | Impact Engineering | Medium | 1 | Repair 11/1 heater Bld. 42 | Yes | Yes | Yes | Yes | 2
2021-07-15 | 11:20 | 7193332 |  |  | 8:50 |  | Impact Engineering | Medium | 1 | Repair 11/1 heater Bld. 42 | Yes | Yes | Yes | Yes | 2
2021-07-15 | 13:30 | 7193332 |  |  | 8:50 |  | Impact Engineering | Medium | 1 | Repair 11/1 heater Bld. 42 | Yes | Yes | Yes | Yes | 2
2021-07-15 | 7:49 | 7193821 |  |  | 7:30 |  | Cleanaway | Medium | 1 | Clean slurry from Lake Duck 25A | No | Yes | Yes | No | 2
2021-07-15 | 11:00 | 7193821 |  |  | 7:50 |  | Cleanaway | Medium | 1 | Clean slurry from Lake Duck 25A | No | Yes | Yes | No | 2
2021-07-15 | 13:10 | 7193821 |  |  | 7:50 |  | Cleanaway | Medium | 1 | Clean slurry from Lake Duck 25A | No | Yes | Yes | No | 2
2021-07-16 | 14:19 | 717153 |  |  | 6:30 | 14:20 | UGL Mech | High | 1 | Drill holes for locking pins | Yes | Yes | Yes | Yes | 2
2021-07-16 | 7:44 | 7171533 |  |  | 7:30 |  | UGL Mech | High | 1 | Drill holes for valve safety pins | Yes | Yes | Yes | No | 2
2021-07-16 | 12:01 | 7171533 |  |  | 6:30 |  | UGL Mech | High | 1 | Drill holes for valve safety pins | Yes | Yes | Yes | No | 2
2021-07-16 | 11:43 | 7181625 | 87318 |  | 7:00 |  | UGL Scaff | High | 1 | Strip scaffold #51 B.O.T. | No | No | No | Yes | 4
2021-07-16 | 7:00 | 7181625 | 87318 |  | 7:00 |  | UGL Scaff | High | 1 | Strip scaffold #51 B.O.T. | No | Yes | Yes | Yes | 4
2021-07-16 | 8:28 | 7183397 |  |  | 7:00 |  | UGL Scaff | High | 1 | Internal scaffolds #34 Digesters | No | Yes | Yes | No | 5
2021-07-16 | 12:10 | 7188546 |  |  | 10:25 |  | ALS Ropes | High | 1 | Routine testing 25A | No | Yes | Yes | Yes | 2
2021-07-16 | 11:21 | 7188644 | 92026 |  | 6:30 |  | UGL Scaff | High | 1 | #6 Mill c/out K.G.A. valve | No | No | No | Yes | 2
2021-07-16 | 8:08 | 7188644 | 92026 |  | 7:00 |  | UGL Scaff | High | 1 | #6 Mill c/out K.G.A. valve | Yes | Yes | Yes | Yes | 2
2021-07-16 | 11:25 | 7191411 | 91815 |  | 8:45 |  | UGL Rope | High | 1 | Replace DSM segment #5 mill | No | Yes | Yes | Yes | 3
2021-07-16 | 13:43 | 7191411 | 91815 |  | 8:45 |  | UGL Rope | High | 1 | Replace DSM segment #5 mill | No | Yes | Yes | Yes | 3
2021-07-16 | 7:00 | 7192350 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 3
2021-07-16 | 11:54 | 7192350 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11A digester vessel | Yes | Yes | Yes | Yes | 3
2021-07-16 | 7:13 | 7192351 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 3
2021-07-16 | 11:54 | 7192351 |  |  | 7:00 |  | UGL Mech | High | 1 | Install liners 11B digester vessel | Yes | Yes | Yes | Yes | 3
2021-07-16 | 8:15 | 7192851 | 92386 |  | 7:40 |  | UGL Scaff | High | 1 | C/out #5 mill boxed bend | No | Yes | No | No | 3
2021-07-16 | 11:10 | 7192851 | 92386 |  | 7:40 |  | UGL Scaff | High | 1 | C/out #5 mill boxed bend | No | Yes | No | No | 3
2021-07-16 | 12:13 | 718707465 |  |  | 12:15 |  | Allrubber | High | 1 | Splice Mill #4 feed conveyor | No | Yes | Yes | Yes | 3
2021-07-16 | 13:55 | 718707465 |  |  | 12:14 |  | Allrubber | High | 1 | Splice Mill #4 feed conveyor | No | Yes | Yes | Yes | 3
2021-07-16 | 7:32 | 7191421 | 91925 |  | 7:00 |  | Thor | Medium | 1 | Install LCD screens 108W/30X | Yes | Yes | Yes | Yes | 2
2021-07-16 | 10:45 | 7191421 | 91925 |  | 7:00 |  | Thor | Medium | 1 | Install LCD screens 108W/30X | Yes | Yes | Yes | Yes | 2
2021-07-16 | 13:05 | 7191421 | 91925 |  | 7:00 |  | Thor | Medium | 1 | Install LCD screens 108W/30X | Yes | Yes | Yes | Yes | 2
2021-07-16 | 7:19 | 7192452 | 82775 |  | 7:00 |  | ALS | Medium | 1 | Routine NDT Bld. 30 | No | Yes | Yes | No | 2
2021-07-16 | 9:00 | 7192452 | 82775 |  | 7:00 |  | ALS | Medium | 1 | Routine NDT Bld. 30 | No | Yes | Yes | No | 2
2021-07-16 | 13:30 | 7192452 | 82775 |  | 7:00 |  | ALS | Medium | 1 | Routine NDT Bld. 30 | No | Yes | Yes | No | 2
2021-07-16 | 7:45 | 7193332 |  |  | 7:30 |  | Impact Engineering | Medium | 1 | Repair 11/1 heater Bld. 42 | No | Yes | Yes | Yes | 2
2021-07-16 | 11:00 | 7193332 |  |  | 7:30 |  | Impact Engineering | Medium | 1 | Repair 11/1 heater Bld. 42 | No | Yes | Yes | Yes | 2
2021-07-19 | 13:25 | 7143978 | 92178 |  | 7:15 | 13:30 | Altrad | High | 2 | Erect scaffold 35R tank for cladding repair | No | No | No | Yes | 3
2021-07-19 | 8:21 | 7143978 | 92178 |  | 7:15 |  | Altrad | High | 2 | Erect scaffold 35R tank for cladding repair | No | Yes | Yes | Yes | 3
2021-07-19 | 8:55 | 7169199 |  |  | 7:30 |  | UGL Mech | High | 2 | Replace Biox supply line bld. 35 | Yes | Yes | Yes | No | 2
2021-07-19 | 10:30 | 7169199 |  |  | 7:30 |  | UGL Mech | High | 2 | Replace Biox supply line bld. 35 | Yes | Yes | Yes | No | 2
2021-07-19 | 22:04 | 7169199 |  |  | 7:30 | 16:00 | UGL Mech | High | 2 | Replace Biox supply line bld. 35 | Yes | Yes | Yes | No | 2
2021-07-19 | 7:50 | 7188448 | 91701 |  | 7:55 | 14:13 | UGL Rope | High | 1 | #34 s/trap. Burn holes in stiffener | Yes | Yes | Yes | Yes | 3
2021-07-19 | 8:34 | 7191128 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean BLD. 35 mud troughs | Yes | Yes | Yes | No | 4
2021-07-19 | 14:20 | 7194254 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean #13 Mud thickener tank | No | No | Yes | No | 3
2021-07-19 | 9:11 | 7194254 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean #13 Mud thickener tank | No | Yes | Yes | No | 3
2021-07-19 | 10:21 | 7194254 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean #13 Mud thickener tank | No | Yes | Yes | Yes | 3
2021-07-19 | 10:00 | 7185218 |  |  | 7:00 | 13:17 | Veolia | Medium | 2 | Replace Potable water line at VTAT offices | Yes | Yes | Yes | No | 3
2021-07-20 | 8:18 | 7166004 |  |  | 7:00 | 13:10 | UGL Elec | High | 2 | Install electrical cable | Yes | Yes | Yes | No | 3
2021-07-20 | 7:45 | 7169199 |  |  | 7:30 | 11:00 | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | Yes | 3
2021-07-20 | 8:15 | 7176446 |  |  | 7:30 |  | Cleanaway | High | 2 | HPW clean #13 Mud thickener tank | Yes | No | Yes | No | 5
2021-07-20 | 11:25 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean #13 mud thickener tank | Yes | Yes | Yes | No | 5
2021-07-20 | 14:19 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 5
2021-07-20 | 9:00 | 7185218 |  |  | 7:00 | 13:15 | Thor | High | 2 | Replace potable water line at VTAT offices | Yes | Yes | Yes | No | 2
2021-07-20 | 7:35 | 7191128 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW . Clean Bld. 35 Mud troughs | Yes | Yes | Yes | No | 6
2021-07-20 | 11:19 | 7191128 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean Bld #35 Mud troughs | No | Yes | Yes | Yes | 6
2021-07-20 | 14:03 | 7191128 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean Bld. #35 Mud troughs | No | Yes | Yes | Yes | 6
2021-07-20 | 7:30 | 7185218 |  |  | 7:00 |  | Thor | Medium | 2 | Replace Potable water line at VTAT offices | Yes | Yes | Yes | No | 2
2021-07-21 | 11:20 | 7163168 |  |  | 6:30 |  | UGL Mech | High | 2 | Install new lime line | Yes | Yes | Yes | No | 5
2021-07-21 | 13:56 | 7163168 |  |  | 6:30 | 15:51 | UGL Mech | High | 2 | Install new lime line | Yes | Yes | Yes | No | 5
2021-07-21 | 7:56 | 7163168 |  |  | 6:30 |  | UGL Mech | High | 2 | Install new lime line | Yes | Yes | Yes | Yes | 5
2021-07-21 | 7:43 | 7166004 |  |  | 6:30 | 12:30 | UGL Elec | High | 2 | Run cable to precoat pumps | Yes | Yes | Yes | No | 3
2021-07-21 | 8:23 | 7169199 |  |  | 7:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 3
2021-07-21 | 11:01 | 7169199 |  |  | 7:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 4
2021-07-21 | 13:40 | 7169199 |  |  | 7:30 | 16:00 | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 4
2021-07-21 | 8:11 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 5
2021-07-21 | 11:25 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 0
2021-07-21 | 13:50 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 0
2021-07-21 | 8:28 | 7191185 |  |  | 7:30 |  | Cleanaway | High | 2 | Clean Bld 35 mud troughs and floor | Yes | Yes | Yes | No | 6
2021-07-21 | 11:05 | 7191185 |  |  | 7:30 |  | Cleanaway | High | 2 | Clean Bld 35 Mud troughs and floor | No | No | No | No | 6
2021-07-21 | 7:00 | 7185218 |  |  | 6:30 |  | Thor | Medium | 2 | Replace potable water line, earthworks | No | No | No | No | 3
2021-07-21 | 9:28 | 7185218 |  |  | 6:30 |  | Thor | Medium | 2 | Replace potable water line, earthworks | No | No | No | No | 3
2021-07-21 | 11:50 | 7185218 |  |  | 6:30 | 14:00 | Thor | Medium | 2 | Replace potable water line. Earthworks | No | No | No | No | 3
2021-07-21 | 12:14 | 7188768 | 90223 |  | 6:30 | 14:30 | Thor | Medium | 2 | Refurbish VTAT transportable | Yes | Yes | Yes | No | 2
2021-07-21 | 14:14:00 PM | 7188768 | 90223 |  | 6:30 | 14:30 | Thor | Medium | 2 | Refurbish VTAT Transportable | Yes | Yes | Yes | No | 2
2021-07-22 | 7:55 | 7163168 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace lime line | Yes | Yes | Yes | Yes | 2
2021-07-22 | 11:18 | 7163168 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace lime line | Yes | Yes | Yes | Yes | 2
2021-07-22 | 14:15 | 7163168 |  |  | 6:30 | 16:00 | UGL Mech | High | 2 | Replace lime line | Yes | Yes | Yes | Yes | 2
2021-07-22 | 8:19 | 7166002 |  |  | 6:30 | 14:00 | UGL Elec | High | 2 | Run new cables to precoat pumps | Yes | Yes | Yes | No | 3
2021-07-22 | 12:00 | 7166002 |  |  | 6:30 |  | UGL Elec | High | 2 | C/Out water heater | Yes | Yes | Yes | No | 2
2021-07-22 | 7:30 | 7169199 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 2
2021-07-22 | 11:00 | 7169199 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 2
2021-07-22 | 14:30 | 7169199 |  |  | 6:30 | 15:00 | UGL Mech | High | 2 | Replace Biox Line | Yes | Yes | Yes | Yes | 2
2021-07-22 | 8:04 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 6
2021-07-22 | 14:20 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 5
2021-07-22 | 11:21 | 7176446 |  |  | 7:00 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 6
2021-07-22 | 14:26 | 7179410 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean mud troughs | No | No | No | No | 3
2021-07-22 | 14:29 | 7179410 |  |  | 7:00 |  | Cleanaway | High | 2 | Clean #46 press | No | No | Yes | No | 3
2021-07-22 | 8:59 | 7179410 |  |  | 6:30 |  | Cleanaway | High | 2 | Clean #46 KFP | Yes | Yes | Yes | No | 3
2021-07-22 | 11:39 | 7179410 |  |  | 7:00 |  | Cleanaway | High | 2 | HPW clean #46 Press | Yes | Yes | Yes | No | 3
2021-07-22 | 8:49 | 7184806 | 90350 |  | 6:30 |  | UGL Mech | High | 2 | Install spool 37A #2 OFT | Yes | Yes | Yes | No | 3
2021-07-22 | 11:35 | 7184806 | 90350 |  | 6:30 |  | UGL Mech | High | 2 | Install spool 37A #2 OFT | Yes | Yes | Yes | No | 3
2021-07-22 | 14:30 | 7184806 |  |  | 6:30 | 14:30 | UGL Mech | High | 2 | Install spool 37A #2 OFT | Yes | Yes | Yes | No | 3
2021-07-22 | 11:49 | 7191185 |  |  | 7:00 |  | Cleanaway | High | 2 | Clean Mud troughs | No | Yes | Yes | No | 4
2021-07-22 | 8:33 | 7191185 |  |  | 7:00 |  | Cleanaway | High | 2 | Clean Bld. 35 mud troughs | Yes | Yes | Yes | No | 4
2021-07-22 | 10:30 | 7185218 |  |  | 7:00 |  | Thor | Medium | 2 | Earthworks and Potable water line repair | Yes | Yes | Yes | No | 5
2021-07-22 | 7:08 | 7185218 |  |  | 7:00 |  | Thor | Medium | 2 | Earthworks for poatable water line | Yes | Yes | Yes | Yes | 3
2021-07-22 | 13:50 | 7185218 |  |  | 7:00 | 14:20 | Thor | Medium | 2 | Repair potable water line | Yes | Yes | Yes | Yes | 2
2021-07-22 | 7:08 | 7188768 |  |  | 6:30 |  | Thor | Medium | 2 | Refurbish transportable at VTAT | Yes | Yes | Yes | No | 2
2021-07-22 | 10:28 | 7188768 |  |  | 6:30 |  | Thor | Medium | 2 | Refurbish transportable hut | Yes | Yes | Yes | No | 2
2021-07-22 | 10:28 | 7188768 |  |  | 6:30 |  | Thor | Medium | 2 | Refurbish transportable hut | Yes | yes | Yes | No | 2
2021-07-22 | 13:54 | 7188768 |  |  | 6:30 | 14:20 | Thor | Medium | 2 | Refurbish transportable | Yes | Yes | Yes | Yes | 1
2021-07-23 | 7:50 | 7166002 |  |  | 7:00 | 11:45 | UGL Elec | High | 2 | Rewire precoat pumps | No | Yes | Yes | No | 2
2021-07-23 | 8:31 | 7169199 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace Biox line | No | Yes | Yes | No | 3
2021-07-23 | 11:25 | 7169199 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 3
2021-07-23 | 11:20 | 7169199 |  |  | 6:30 |  | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 3
2021-07-23 | 18:50 | 7169199 |  |  | 6:30 | 15:00 | UGL Mech | High | 2 | Replace Biox line | Yes | Yes | Yes | No | 3
2021-07-23 | 11:41 | 7176446 |  |  | 7:30 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 5
2021-07-23 | 14:00 | 7176446 |  |  | 7:30 |  | Cleanaway | High | 2 | Descale #13 Thickener | Yes | Yes | Yes | No | 5
2021-07-23 | 8:51 | 7176496 |  |  | 7:30 |  | Cleanaway | High | 2 | Descale F13 Thickener | No | Yes | Yes | No | 4
2021-07-23 | 8:20 | 7184806 | 90350 |  | 7:20 |  | UGL Mech | High | 2 | Install spool 37A #2 OFT. | No | Yes | Yes | No | 2
2021-07-23 | 12:01 | 7184806 | 90350 |  | 7:20 |  | UGL Mech | High | 2 | Install spool 37A2 OFT | Yes | Yes | Yes | No | 2
2021-07-23 | 13:50 | 7184806 | 90350 |  | 7:20 | 14:00 | UGL Mech | High | 2 | Install spool 37A2 OFT | Yes | Yes | Yes | No | 2
2021-07-23 | 13:45 | 7191185 |  |  | 8:00 |  | Cleanaway | High | 2 | Clean mud troughs | No | No | Yes | No | 6
2021-07-23 | 8:02 | 7191185 |  |  | 8:00 |  | Cleanaway | High | 2 | Clean mud troughs | No | Yes | Yes | No | 3
2021-07-23 | 11:54 | 7191185 |  |  | 8:00 |  | Cleanaway | High | 2 | Clean mud troughs | Yes | Yes | Yes | No | 6
2021-07-23 | 9:30 |  | 90234 |  | 7:50 |  | UGL Elec | Low | 2 | Rewire VTAT transportable | No | No | Yes | No | 1
2021-07-23 | 11:03 |  | 90234 |  | 7:50 |  | UGL Elec | Low | 2 | Rewire VTAT transportable | Yes | Yes | Yes | No | 1
2021-07-23 | 13:05 |  | 90234 |  | 7:50 | 14:00 | UGL Elec | Low | 2 | Rewire VTAT transportable | Yes | Yes | Yes | No | 3
2021-07-23 | 9:00 | 7165866 |  |  | 7:40 | 11:00 | Cleanaway | Medium | 2 | Build sand bund | Yes | Yes | Yes | Yes | 2
2021-07-23 | 7:30 | 7185218 |  |  | 7:15 |  | Veolia | Medium | 2 | Repair potable water line | No | Yes | Yes | No | 2
2021-07-23 | 13:20 | 7185218 |  |  | 10:00 | 14:00 | Thor | Medium | 2 | Earthworks Potable water line | No | No | No | Yes | 4
2021-07-23 | 11:25 | 7198275 |  |  | 10:00 |  | Thor | Medium | 2 | Earth works on potable water line | No | No | No | Yes | 2
2021-07-26 | 9:15 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 50 S/Blast | Yes | Yes | Yes | No | 3
2021-07-26 | 11:19 | 7129630 |  |  | 7:30 | 11:20 | Kaefer | High | 3P | Precip 50 S/Blast | Yes | Yes | Yes | No | 3
2021-07-26 | 9:25 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Replace Floor | Yes | Yes | Yes | Yes | 4
2021-07-26 | 11:02 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Replace Floor | Yes | Yes | Yes | Yes | 3
2021-07-26 | 8:47 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Install drains Building 50 | Yes | Yes | Yes | Yes | 2
2021-07-26 | 11:30 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Install drains Building 50 | Yes | Yes | Yes | Yes | 2
2021-07-26 | 14:00 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Install drains Building 50 | Yes | Yes | Yes | Yes | 2
2021-07-26 | 8:40 | 721356 |  |  | 8:00 |  | Cooling Towers WA | Medium | 3C | Cleaning cold water basin | Yes | Yes | Yes | No | 4
2021-07-26 | 10:38 | 721356 |  |  | 8:00 |  | Cooling Towers WA | Medium | 3C | Cleaning cold water basin | Yes | Yes | Yes | No | 4
2021-07-26 | 11:59 | 7133470 |  |  | 7:30 | 12:00 | ALS | Medium | 3C | Thermal Imaging Calciner 3 | No | Yes | Yes | Yes | 3
2021-07-26 | 10:30 | 7133470 |  |  | 7:30 | 12:00 | ALS | Medium | 3C | Thermal Imaging Calciner 3 | Yes | Yes | Yes | Yes | 3
2021-07-26 | 8:57 | 7135408 |  |  | 8:00 | 11:00 | ALS | Medium | 3C | Routine vibration test | No | Yes | Yes | No | 1
2021-07-26 | 10:50 | 7186763 |  |  | 9:30 |  | UGL Elec | Medium | 3P | Install lights 45 CWT Pump | No | Yes | Yes | No | 2
2021-07-26 | 8:24 | 7189882 | 91979 |  | 7:30 |  | UGL Mech | Medium | 3C | 50S SST001 Open | Yes | Yes | Yes | No | 5
2021-07-26 | 10:46 | 7189882 | 91979 |  | 7:30 |  | UGL Mech | Medium | 3C | 50S SST001 Open | Yes | Yes | Yes | No | 5
2021-07-26 | 13:35 | 7189882 | 91979 |  | 7:30 |  | UGL Mech | Medium | 3C | 50S SST001 Open | Yes | Yes | Yes | No | 5
2021-07-26 | 8:30 | 7191268 | 91971 |  | 8:00 |  | Cleanaway | Medium | 3C | Vacuum Superfine | Yes | Yes | Yes | Yes | 4
2021-07-26 | 10:52 | 7191268 | 91971 |  | 8:00 |  | Cleanaway | Medium | 3C | Vacuum Superfine | Yes | Yes | Yes | Yes | 5
2021-07-26 | 13:30 | 7191268 | 91971 |  | 8:00 |  | Cleanaway | Medium | 3C | Vacuum Superfine | Yes | Yes | Yes | Yes | 5
2021-07-26 | 8:15 | 7194166 |  |  | 7:30 |  | UGL Mech | Medium | 3C | Install 3 Way V/V S | Yes | Yes | No | No | 2
2021-07-26 | 11:07 |  | 86161 |  | 11:00 |  | ALS | Medium | 3P | PT 155 MP1 | No | Yes | Yes | Yes | 1
2021-07-26 | 13:16 |  | 86161 |  | 11:00 |  | ALS | Medium | 3P | PT 155 MP1 | No | Yes | Yes | Yes | 2
2021-07-27 | 7:20 | 4321494 | 85618 |  | 7:30 |  | UGL Scaff | High | 3C | Scaffold Filter 12 Stack | Yes | Yes | Yes | No | 4
2021-07-27 | 10:58 | 4321494 | 85618 |  | 7:30 |  | UGL Scaff | High | 3C | Scaffold Filter 12 Stack | Yes | Yes | Yes | No | 4
2021-07-27 | 8:00 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 155 Repair Floor | Yes | Yes | Yes | No | 5
2021-07-27 | 10:52 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 155 Repair Floor | Yes | Yes | Yes | No | 4
2021-07-27 | 14:00 | 7160784 |  |  | 7:30 | 16:00 | Kaefer | High | 3P | Precip 155 Repair Floor | Yes | Yes | Yes | No | 4
2021-07-27 | 7:15 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Repair Drainage | No | Yes | Yes | Yes | 6
2021-07-27 | 11:42 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Repair Drainage | No | Yes | Yes | Yes | 6
2021-07-27 | 14:00 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Repair Drainage | No | Yes | Yes | Yes | 6
2021-07-27 | 10:38 | 7197297 |  |  | 10:00 | 13:00 | Veolia | High | 3P | HPW 45 A 3 Dropper | Yes | Yes | Yes | No | 3
2021-07-27 | 13:00 |  |  |  | 11:30 | 15:00 | Kaefer | High | 3P | S/Blast #50 Precip | Yes | Yes | Yes | No | 3
2021-07-27 | 7:30 | 7135408 |  |  | 7:10 | 11:00 | ALS | Medium | 3P | Routine vibration testing BLD44 | No | Yes | Yes | No | 1
2021-07-27 | 7:00 | 7191268 | 91971 |  | 6:30 |  | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | No | 3
2021-07-27 | 11:10 | 7191268 | 91971 |  | 6:30 |  | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | Yes | 3
2021-07-27 | 13:30 | 7191268 | 91971 |  | 6:30 | 18:30 | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | Yes | 3
2021-07-27 | 8:46 | 7193095 | 92061 |  | 7:30 |  | UGL Elec | Medium | 3C | Replace lights | No | Yes | Yes | No | 2
2021-07-27 | 11:00 | 7193095 | 92061 |  | 7:30 |  | UGL Elec | Medium | 3C | Replace lights | No | Yes | Yes | No | 2
2021-07-27 | 13:55 | 7193095 | 92061 |  | 7:30 | 14:30 | UGL Elec | Medium | 3C | Replace lights | No | Yes | Yes | No | 2
2021-07-27 | 11:26 |  | 95047 |  | 7:30 | 14:30 | UGL Scaff | Medium | 3P | Build scaff 63 & 115 Launder | Yes | Yes | Yes | No | 3
2021-07-27 | 13:30 |  | 95047 |  | 7:30 | 14:30 | UGL Scaff | Medium | 3P | Build scaff 63 & 115 Launder | Yes | Yes | Yes | No | 2
2021-07-28 | 7:30 | 4321494 | 85618 |  | 6:45 |  | UGL Scaff | High | 3C | #12 Stack Erect Scaffolding | Yes | Yes | Yes | No | 4
2021-07-28 | 10:40 | 4321494 | 85618 |  | 6:45 |  | UGL Scaff | High | 3C | #12 Stack Erect Scaffolding (Rained Off) | Yes | Yes | Yes | No | 0
2021-07-28 | 8:30 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 50 Repairs | Yes | Yes | Yes | No | 4
2021-07-28 | 11:26 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 50 Repairs | Yes | Yes | Yes | No | 4
2021-07-28 | 13:50 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | Precip 50 Repairs | Yes | Yes | Yes | No | 4
2021-07-28 | 8:20 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | Precip I55 Repair Floor | Yes | Yes | Yes | Yes | 4
2021-07-28 | 11:17 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | Precip I55 Repair Floor | Yes | Yes | Yes | No | 4
2021-07-28 | 14:12 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | Precip I55 Repair Floor | Yes | Yes | Yes | No | 4
2021-07-28 | 14:30 | 7172256 |  |  | 7:00 |  | WBHO | High | 3C | Repair Drainage | No | No | Yes | Yes | 5
2021-07-28 | 7:15 | 7172256 |  |  | 7:00 |  | WBHO | High | 3C | Repair Drainage | No | Yes | Yes | Yes | 5
2021-07-28 | 10:30 | 7172256 |  |  | 7:00 |  | WBHO | High | 3C | Repair Drainage | No | Yes | Yes | Yes | 5
2021-07-28 | 10:20 | 7180452 | 82507 |  | 7:31 | 11:52 | Konecranes | High | 3C | Service cranes | Yes | Yes | Yes | No | 1
2021-07-28 | 14:18 | 7189882 | 91979 |  | 7:20 |  | UGL Mech | High | 3C | 5OS Repairs SST001 | Yes | Yes | Yes | No | 4
2021-07-28 | 14:00 |  |  |  | 10:01 | 14:30 | UGL Rope | High | 3P | Weld Repairs #50 Precip | No | Yes | Yes | No | 4
2021-07-28 | 7:00 | 7191268 | 91971 |  | 6:30 |  | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | Yes | 3
2021-07-28 | 10:15 | 7191268 | 91971 |  | 6:30 |  | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | Yes | 3
2021-07-28 | 14:25 | 7191268 | 91971 |  | 6:30 |  | Cleanaway | Medium | 3C | Vacuum Superfines | No | Yes | Yes | Yes | 3
2021-07-28 | 8:05 |  | 86161 |  | 8:00 |  | ALS | Medium | 3P | MP1 I55 Precip | No | Yes | Yes | No | 2
2021-07-28 | 11:10 |  | 86161 |  | 8:00 |  | ALS | Medium | 3P | MP1 I55 Precip | No | Yes | Yes | No | 4
2021-07-28 | 14:10 |  | 86161 |  | 8:00 |  | ALS | Medium | 3P | MP1 I55 Precip | No | Yes | Yes | No | 2
2021-07-29 | 8:47 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | #50 Precip Blast | No | Yes | Yes | No | 3
2021-07-29 | 10:40 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | #50 Precip Blast | Yes | Yes | Yes | No | 3
2021-07-29 | 13:45 | 7129630 |  |  | 7:30 |  | Kaefer | High | 3P | #50 Precip Blast | Yes | Yes | Yes | No | 3
2021-07-29 | 8:00 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Repairs | Yes | Yes | Yes | No | 4
2021-07-29 | 10:47 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Repairs | Yes | Yes | Yes | No | 4
2021-07-29 | 11:15 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Repairs | Yes | Yes | Yes | No | 4
2021-07-29 | 13:50 | 7160784 |  |  | 7:30 |  | Kaefer | High | 3P | 155 Precip Repairs | Yes | Yes | Yes | No | 4
2021-07-29 | 7:30 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Drain repairs | No | No | Yes | Yes | 5
2021-07-29 | 9:20 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Drain repairs | No | No | Yes | Yes | 5
2021-07-29 | 11:04 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Drain repairs | No | No | Yes | Yes | 5
2021-07-29 | 14:20 | 7172256 |  |  | 7:30 |  | WBHO | High | 3C | Drain repairs | No | No | Yes | Yes | 5
2021-07-29 | 8:21 | 7189882 | 91979 |  | 7:00 | 10:00 | UGL Mech | High | 3C | SST001 FBT I | Yes | Yes | Yes | No | 3
2021-07-29 | 10:45 | 7189882 | 91979 |  | 7:00 | 10:00 | UGL Mech | High | 3C | SST001 FBT I | Yes | Yes | Yes | No | 3
2021-07-29 | 10:58 | 7135408 |  |  | 9:00 | 12:00 | ALS | Medium | 3P | Vibration Analysis | No | Yes | Yes | No | 1
2021-07-29 | 9:02 | 7185142 |  |  | 8:00 |  | Cleanaway | Medium | 3P | Reclaim Hydrate | No | Yes | Yes | No | 2
2021-07-29 | 10:47 | 7185142 |  |  | 8:00 |  | Cleanaway | Medium | 3P | Reclaim Hydrate | No | Yes | Yes | No | 2
2021-07-29 | 14:00 | 7185142 |  |  | 8:00 |  | Cleanaway | Medium | 3P | Reclaim Hydrate | No | Yes | Yes | No | 2
2021-07-29 | 11:39 | 7194450 | 92716 |  | 11:40 |  | UGL Elec | Medium | 3C | Check power outlets | Yes | Yes | Yes | No | 2
2021-07-29 | 13:27 | 7194490 | 92625 |  | 7:30 |  | UGL Elec | Medium | 3P | Replace lights | No | No | Yes | No | 2
2021-07-29 | 8:00 |  | 86161 |  | 8:00 | 10:00 | ALS | Medium | 3P | FBTI Precip I55 | Yes | Yes | Yes | No | 1
Note on A1: Cullen, Joshua: Date Format Short DD/MM
Note on B1: Cullen, Joshua: 24hr (HH:MM)
Note on E1: Cullen, Joshua: Work Orders can be: (a) 1234567 or (b) WO1234567 or a Project Number (c) PIN0001234567
Note on F1: Cullen, Joshua: 24hr (HH:MM)
Note on G1: Cullen, Joshua: 24hr (HH:MM)
Note on M1: Cullen, Joshua: Yes or No
Note on N1: Cullen, Joshua: Yes or No
Note on O1: Cullen, Joshua: Yes or No

## print copy (hidden)
CONTRACTOR WORKS MANAGEMENT ¦ JOB LOG
Date | Observation Time | Purchase Order Number | RCS Number | Work Order Number | Job Start Time | Job Finish Time | Work group | Risk | OC | Authority To Proceed Description | Alcoa Responsible Person | Contractor Responsible Person | Does ARP walk the job. In the alloted time frames | Field Verifications Completed (ARP) | Field Verifications Completed (CRP) | Supervision Present | Name Of Supervisor | Names Of People On Job 1 | Names Of People On Job 2 | Names Of People On Job 3 | Names Of People On Job 4 | Names Of People On Job 5 | Names Of People On Job 6 | Names Of People On Job 7 | Names Of People On Job 8 | Names Of People On Job 9 | Names Of People On Job 10 | Equipment On Job 1 | Equipment On Job 2 | Equipment On Job 3 | Equipment On Job 4 | Equipment On Job 5 | Equipment On Job 6 | Equipment On Job 7 | Equipment On Job 8 | Equipment On Job 9 | Equipment On Job 10
Note on A2: Cullen, Joshua: Date Format Short DD/MM
Note on B2: Cullen, Joshua: 24hr (HH:MM)
Note on E2: Cullen, Joshua: Work Orders can be: (a) 1234567 or (b) WO1234567 or a Project Number (c) PIN0001234567
Note on F2: Cullen, Joshua: 24hr (HH:MM)
Note on G2: Cullen, Joshua: 24hr (HH:MM)
Note on O2: Cullen, Joshua: Yes or No
Note on P2: Cullen, Joshua: Yes or No
Note on Q2: Cullen, Joshua: Yes or No
Note on AC2: Cullen, Joshua: Restrict Equipment to Vehicles (ute, truck, HPW unit & size, VAC truck and anything else worth noting)

## Observations made (hidden)
Observations Made
ATPs Not having sign on times recorded
Task #35 canned shortly after commencement.
Task #49 canned shortly after commencement.
Task #64 stopped due to holed slurry pipe. Airborne Caustic mist. | stopped due to holed slurry sand trap feed line spraying caustic mist over work area. Stopped 13:00
Task #71 | stopped due to holed slurry sand trap feed line spraying caustic mist over work area. Stopped 13:00
Task #73 | stopped due to holed slurry sand trap feed line spraying caustic mist over work area. Stopped 13:00
OPC1 group leaders in 108w sign ATP's in their offices . This statement freely admitted.
Start times booked by contractors differ from actual start times as ARP's are often tied up in meetings and contractors have to wait. Sometimes over an hour.
Heater changes in OPC#1 occur daily and most last over an hour. Are down times booked ? Or crews move to other areas. |  |  |  | crews moved on to other tasks. | ed
ATPs Signed by ARPs without P/O number noted on forms.
Tasks 92 &93. Crews started 06:30 but briefing not given till 09:00
Task 94 crew start at 06:30 in Pinjarra W/shop. No person available to sign ATP until 09:15 on job.
ALS checks on a routine basis cover an entire floor of a building which would take the ARP ( normally a group leader.) too long to go over with the technician as compared to a single task on a particular piece of equipment. Currently the A.T.Ps for ALS routine checks are signed in the group leaders office and are always rated Medium so only require one signature a shift. The issues (current work and dangers) in the building are relayed to the techician at the ATP signing.
Tasks 161/162 delayed 3 hours due to unit being restricted.
Task 163 not started until 12:00 due to isolation and lack of crane.
Task 158. Crew on job at 0630 ,inspected job then collected gear. Assigned another task and unloade scaffold then left at 13:18. Crew member stated that supervisor had visited the job Twice when I asked about supervision.
Contractors board in 30X control room only 50 % correct. Magnetic labels left in position after jobs completed.
Task 218 Crane shared with area maint on other mill #5 work.
Task 219 07:00 to 19:00 then N/S around the clock.
Task 226 A; Day 15:00 finish. M. Ray 16:00 finish
Task 227 Finish 19:00 then N/S around the clock
Task 230 Crew on job 07:15. CSE briefing not completed until 09:30 |  | 7:30 | . CSE not on until 09:35
Task 234 restricted for high level of thickener #23
Tasks 233 and 237 stopped early due to rain too heavy to operate EWPs.
task 238 | delayed several hours due to area restrictions.
Are contractor start times from start of tool box meetings, Turn up on the job or after ATPs signed.
Task 242 ATP signed 07:00
Task 243 ATP signed 07:30
Task 244 ATP signed 08:00
Task 255 No personnel on job 13:45
Task 259 ATP signed 07:40
Task 258 ATP signed 08:30
Task 260 ATP signed 07:00
Task 266 ATP form now with Veolia, When they leave the jobin thier ute the form goes with them instead of staying with the sub contractor which is doing most of the work.
Task 265 | ATP signed o7:55
Both HPW jobs in Bld. 35 do not have ATPs checked after initial morning signing by ARP and both are high risk tasks. Contractors should stop tasks until they are as on other sites. Or phone ARP.
Thor will say that they knock off at a certain time but when I check within that time frame on ATPs on two occasions they have already packed up.
Task 279 | One descaler left inbetween visits and I was told another was also going to leave prior to working his 12 Hr. Shift.
Task 286. C. Whitford on JSA form , but working in yard making supports for same job.
Task 304 Thor subcontracting to Veolia. Started at 10:00 and finished at 14:00. No ATP and No JSA to check against names. Also very difficult to communicate with.

## Filters (hidden)
Yes / No | OC
Yes | 1
No | 2
3C
3P
4
5
6
10

## Charts (hidden)
Count of Observation Time | Column Labels |  |  |  |  | Row Labels | Count of Field Verifications Completed (ARP)
Row Labels | 1 | 2 | 3P | 3C | Grand Total | No | 7.833%
2021-07-05 | 10 |  |  |  | 10 | Yes | 92.17%
2021-07-06 | 11 |  |  |  | 11 | Grand Total | 100%
2021-07-07 | 30 |  |  |  | 30
2021-07-08 | 19 |  |  |  | 19
2021-07-09 | 16 |  |  |  | 16
2021-07-12 | 25 |  |  |  | 25
2021-07-13 | 31 |  |  |  | 31
2021-07-14 | 25 |  |  |  | 25
2021-07-15 | 22 |  |  |  | 22
2021-07-16 | 27 |  |  |  | 27
2021-07-19 | 1 | 10 |  |  | 11
2021-07-20 |  | 10 |  |  | 10
2021-07-21 |  | 17 |  |  | 17
2021-07-22 |  | 27 |  |  | 27
2021-07-23 |  | 21 |  |  | 21
2021-07-26 |  |  | 7 | 15 | 22
2021-07-27 |  |  | 8 | 11 | 19
2021-07-28 |  |  | 10 | 10 | 20
2021-07-29 |  |  | 13 | 7 | 20
Grand Total | 217 | 85 | 38 | 43 | 383